## Launching
NO | Description OF Scenario | Heading On Home Page | Section Position | File Name | Status | Payment Type | Diet Plan Checked | Weekly Checkup Checked | Plan Amount | Paid Amount | Discount | User ID | Password | Gender | Status | Commenr
1 | Need to add Transformations section on home page, all before and after images should be visible on slider | TRANSFORMATION RESULTS | Should be after ABOUT US section | Transformations | Completed
2 | Need to Add Testimonials on Home Screen, all instagram links will be added which will directly point to Instagram pages | TESTIMONIALS | Should be after Transformation Result Section | Testimonials Folder | Need to discuss
3 | Replace home page slider images with Actual images | Slider before login | Should be on home page | Home Slider Images | Completed
4 | Need to discuss where to add Trainers photos on home page | Not Sure yet | Not Sure Yet | Trainers | Completed
5 | Need to discuss how to add all fun images | Not Sure yet | Not Sure Yet | Fun | Pending
6 | Launchin page - Login Text should be in capital letter | LOGIN | On Top of the Page, right corner |  | Completed
7 | Login with admin user, click on login button |  |  |  | Completed | [6 empty] | 1001 | admin
8 | Login with member user, click on login button |  |  |  | Completed
9 | Login with user name and change password |  |  |  | Completed

## Contact Us
NO | Description OF Scenario | Status | Comment | Developer's Comment | Heading On Home Page | Section Position | File Name | Payment Type | Diet Plan Checked | Weekly Checkup Checked | Plan Amount | Paid Amount | Discount | User ID | Password | Gender | Status | Commenr
1 | Contact Us text should be in Capital Letter | Completed | CONTACT US
2 | Phone Number need to change | Pending |  | Please provide Phone number
3 | Email Id need to change | Completed | hfitabss@gmail.com
4 | Our Location need to be change | Pending |  | Please provide Location
5 | Increase the Size of text box Email ID, Address | Completed | Email Text Box Size Address Line 1, Address Line 2
6 | Add a another text box for adding a description' | Completed | Add Text Box 'Description' where user could add free text' free text should store into database it should reach to the admin email as a text'
7 | Member Added to Enquiry List' should need to change to standard message format | Completed | Once click on OK, button should navigate to HOME Page
8 | CANCEL Buttion, once click, it should navigate back to Home page | Completed | Click on CANCEL button should navigate to HOME Page
9 | Total Lead Count should get increased | Completed
10 | On Dashboard, once click on 'TOTAL LEAD COUNT' , it will navigate to Table | Completed
11 | Add Validation for each fields | Completed | All fields should be mandatory for guest to filled
12 | Description column is needed, in case more than 20 inquiries, add pagination | Completed | Previous 1 ¦ 2 ¦ 3 ¦ Next is a example of pagination
13 | Change HOME to DASHBOARD, on click on DASHBOARD navigate to Dashboard.aspx | Completed | Change HOME to heading 'DASHBOARD', navidate to Dashboard.aspx
14 | Remove About Us and Contact Us | Completed | For Admin, it doesn't make a sense, hence remove these two headers

## Change Password
NO | Description OF Scenario | Design Change On Home Page | Functional Change | Status | File Name | Status | Payment Type | Diet Plan Checked | Weekly Checkup Checked | Plan Amount | Paid Amount | Discount | User ID | Password | Gender | Status | Commenr
1 | Click on Change Password open on new window |  | Yes | Completed
2 | Enter MemberID, New Password, Change Password and click on Change Password button, verify password is changes in DB |  | Yes | Completed
3 | Remove Headers from Change Password.aspx page | Yes |  | Completed
4 | Click on Cancel Button, it will navigate to Login screen |  | Yes | Completed

## Dashboard
Sr No | Description | Design Change | Functional Change | Statgus
1 | Add Heading 'ABSS HFIT MEMBERSHIP MANAGEMENT SOLUTION' on page after Logo |  | Yes | Completed
2 | When user clicks on LOGO, its getting crash, it should direct to Home Page |  | Yes | Completed
3 | Design of all section i.e. 'Active Members' Inactive members, Total Leads Count' | Yes |  | Completed

## Add Member
NO | Description OF Scenario | Status |  | Plan Type | Payment Type | Diet Plan Checked | Weekly Checkup Checked | Plan Amount | Paid Amount | Discount | User ID | Password | Gender | Status | Commenr
scn1 | Click on Add Member button, it will navigate to Membership registration Page | Completed | [12 empty] | Add as button for Add Member | Low Priority
scn2 | Add member as CASH SIX WEEKs | Completed | [10 empty] | Male | Done
scn2 | Add member as CASH SIX Month | Completed | [10 empty] | Female | Done
scn2 | Add member as CASH Three Month | Completed | [10 empty] | Female | Done
scn2 | Add member as CASH Tewlve Month | Completed | [10 empty] | Male | Done
scn2 | Add 20 members, add member without checkup & diet plan check box | Completed | [12 empty] | 1. in case selected 'One Session' plan, plan start and plan end date should be disabled
scn2 | View Member Details click on name of Member | Completed | [10 empty] | Female | Done
scn2 | Add Member as Cheque and Three Month | Pending | Unable to add member with Payment Type as 'Cheque'
scn2 | Unabled to add Member with "ONE SESSION" Plan Type | Pending | Unable to add member with Plan Type "SESSION"
scn2 | Add member with Paid amount and then later enter the discount amount, and submit the member | Pending | when we enter the discount later, it should automatically need duduct from the total amount, and due amount should get calculated
scn2 | Insert a member with option as plan i.e. Session and submit member without entering plan start and end date, make sure select the payment type as 'Cheque' | Completed |  | One Session | Cheque | [7 empty] | Female | Failed | Find screenshot name | End date should be same as start date
scn2 | Edit option to modify Member Details i.e. if user Diet plan and checkup done later, then user is allow to setup it | Pending |  | Six Week | Cash | No | No | [5 empty] | Male | Failed | There is option to edit member details
scn2 | Plan Start date and Plat end date should be ediable only after selection Plan type othervise it should be disabled | Completed |  | Three Month | Cash | yes | No | [5 empty] | Male | Failed | Plan start date is getting selected before selecting a plan from the dropdown | Drop
scn2 | Submit Member without entering an mandatory fields i.e. Name, Email Id, Phone Number, Member Height and Weight', Member Plan, Amount, Birthday and Gender, Payment Type (cash, cheque) etc | Completed |  | Six Month | Cheque | yes | Yes | [5 empty] | Male | Failed | All Fields are mandatory except Emergency Contact Number and Discount | Done - need to checkout
scn2 | In case user tries to enter amount more than plan amount i.e. paid amount > Plan amount, user should get a proper message saying not possible | Pending |  | Six Month | Cheque | yes | Yes | 30000 | 30000 | 1000 |  |  | Male | Failed | Due amount going into -ve amount, in this case its -1000
scn2 | FAT LOSS BY | Pending
scn2 | View Invoice details and download | Completed | [12 empty] | Invoice should open in the window, instead on same window to avoid click on back button
scn2 | Add new invoice and download until its reach to zero | Completed | [12 empty] | Invoice Number should bot ediable, add calender to select invoce date once invoice submitted, popup window need to be modified to standard format
scn2 | view content of the invoice of each downloads | Completed | [12 empty] | Discount amount should be text instead of Final amount add previous paid amount address field on invoice pdf is not visible = show INVOICE 2022Invoice1
scn2 | click on active member on dashboard and verify all table entries on the table | Completed
scn2 | Modiy member tablle entry | Pending | [12 empty] | User is not able to modify the member details
scn2 | Option for user to change password option | Completed
scn2 | Try to add invoice when paid all course fee | Completed | [12 empty] | User is able to submit the invoice on complete paid amount - show Capture-VE Amt
scn2 | add member with payment mode as Cheque | Pending | [11 empty] | Done | Where are we showing cheque details in the appplication
scn2 | Add Unit to Weight and Height and reduce text box size | Completed | [12 empty] | Need a back button to go previous page
UPI image is not require in case of payment mode selected as Cash or Cheque
Qauery | [14 empty] | Need to give label to weigth and Height field - I,e, KG and Inches'
1 | Do we need to show discount on the 2nd row of invoice | [13 empty] | need to add validation on screens i.e. in case user not added value then should show error message in RED
2 | [14 empty] | Cheque fields are not needed in case Payment Mode is selected as Cash or UPI
3 | Add Pagination Option after 20 resources added on the form to view 21st Member | [13 empty] | after clicked on logs validation error failed displayed'
4

## Invoice
NO | Description OF Scenario | Program | MemberID | Invoice Number | User ID | Password | Status | Commenr | Status
scn2 | View Invoice details and download | Six Month | 4026 | 4026Invoice1 |  |  | Minor Change | Invoice should open in the window, instead on same window to avoid click on back button | Completed
scn2 | Add new invoice and download until its reach to zero | Six Month | 4026 | 4026Invoice1 |  |  | Major Change | Invoice Number should bot ediable, add calender to select invoce date once invoice submitted, popup window need to be modified to standard format User is still allow to submit the invoice even if member is paid whole amount (Check Abhinav Bindra's invoices) - screenshot - -ve amount invoice | Completed
scn2 | view content of the invoice of each downloads | Six Month | 4026 | 4026Invoice1 |  |  | Minor Change | Discount amount should be text instead of Final amount add previous paid amount address field on invoice pdf is not visible = show INVOICE 2022Invoice1 | Completed
scn2 | Verify member in Inactive state when plan date expires | Six Month | 5022 | 5022Invoice1 |  |  | Major Change | User is able to submit the invoice on complete paid amount | Completed
scn1 | Verify invoice is not possible for inactive member | Six Month |  |  |  |  | Passed
scn2 | click on active member on dashboard and verify all table entries on the table | [6 empty] | User is not able to modify the member details | Completed
scn2 | Modiy member tablle entry
scn2 | Option for user to change password option | [6 empty] | User is able to submit the invoice on complete paid amount - show Capture-VE Amt | Completed
scn2 | Try to add invoice when paid all course fee | [5 empty] | Done | Where are we showing cheque details in the appplication | Pending
scn2 | add member with payment mode as Cheque | [6 empty] | Need a back button to go previous page | Pending
[8 empty] | UPI image is not require in case of payment mode selected as Cash or Cheque | Completed
[8 empty] | Need to give label to weigth and Height field - I,e, KG and Inches' | Pending
[8 empty] | need to add validation on screens i.e. in case user not added value then should show error message in RED | Pending
[8 empty] | Cheque fields are not needed in case Payment Mode is selected as Cash or UPI | Completed
[8 empty] | after clicked on logs validation error failed displayed' | Pending

## MemberDetails
NO | Description OF Scenario | Status | Program | MemberName | Status (Diet / Checkup) | Personal details (Age, Gender, Weight, Height etc) | Member Information | Password | Commenr
scn1 | verify Member Details i.e. Name, Diet plan, age, Gender, Weight, Height, Status and all tab details i.e. Membership information, Invoice, Weekly Checkup | completed | Three Months | Aniket Shiyal | Yes | Correct |  |  | Current Weight could change only Weight
scn1 | Verify Member Details i.e. Member ship details in case member is Inactive | completed | Six Weeks | Trupti Pashankar | Yes | Correct
scn1 | View Member Details and go back to previous page i.e. Member List Table | Pending | Three Months | Aniket Shiyal | Yes | Correct |  |  | There should be button to go back to the membership list
scn1 | Verify when member plan end date gets expire then status of member is inactive and no invoice will get added | completed | Three Months | Trupti Pashankar | Yes | Correct
scn1 | Verify Member information Correctly Displayed | completed | Three Months | Trupti Pashankar | Yes | Correct
scn1 | Verify Member Information is ediable to User | Pending | Three Months | Trupti Pashankar | Yes | Correct | Correct |  | Member information is not editable to user, it should be i.e. email id, address, Plan if user wants to change it
Scn1 | User should be able to allow user active from inactive state, in case member want to continue membership | Pending | [6 empty] | User is not allow to edit plan, plan start date, end date and make is active from inactive state

## Weekly Checkup
NO | Description OF Scenario | Status | Program | MemberName | Status (Diet / Checkup) | Personal details (Age, Gender, Weight, Height etc) | Weekly Checkup | Measurement | Comment
Scn1 | User is able to add Weekly Checkup parameters for Member | Completed
Scn1 | User is not able to add Weekly Checkup parameters for Inactive Members | Completed | Six Week | Trupti Pashankar | Yes | Yes | Correct |  | User should not allow to add weekly checkup for inactive member
Scn1 | Message 'Weekly Checkup Data Added Successfully' need to in standard format | Pending | Six Week | Trupti Pashankar | Yes | Yes | Correct |  | its not in a standard format
Scn1 | User is not able to add measurement parameterts for inactive members | Completed | Six Week | Trupti Pashankar | Yes | Yes | Correct
Scn1 | Message 'Measurement Data Added Successfully' need to in standard format | Pending | Six Week | Trupti Pashankar | Yes | Yes | Correct |  | its not in a standard format
Scn1 | Once measurement and weekly checkup data submitted by entering all parameters, it close the window and point to Member details page | Pending | Six Week | Trupti Pashankar | Yes | Yes | Correct |  | Its is not pointing to the Measurment in case measurment entered, and to Weekly Checkup in case weekly checkup entered
Scn1 | Add weekly check for active member - 21 rows | Completed | Six Month | Abhinav Bindra | Yes | Yes | Correct
Scn1 | Add Measurment parameters for active members - 21 rows | Completed | Six Month | Abhinav Bindra | Yes | Yes | Correct | Correct | User is not able to edit the measurement fields - eror 'String was not recognized as a valid DateTime' error on the screen
Scn1 | Delete Measurement Entry from the Table | Pending | Six Month | Abhinav Bindra | Yes | Yes | Correct | Correct | Delete gives a exception
Scn1 | Verify Fat Loss By field value (Registration Time Weight - Current Weight) - in case Weigth Loss | Pending | Six Month | Sachin Kumbhar | Yes | Yes | Correct
Scn1 | Verify Fat Loss By field value (Registration Time Weight - Current Weight) - in case Weigth Gain | Pending | Six Month | Abhinav Bindra | Yes | Yes | Correct | Correct | Fat Loss should field should get toggled to Fat Gain, in case increase into the Weigth of member
Scn1 | There should be pagination <Previous, 1,2,3,4, Next> option when records rows gets increase for Weekly checkup and measurments | Pending | Six Month | Abhinav Bindra | Yes | Yes | Correct |  | there is no pagination
Scn1